| Action Items |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Ref | Action Items | Status | Who | Due By | Remarks |
| 5.1 | Registrar – Kaia Meet with Kaia to discuss her role on the NCD SCA as registrar | COMPLETED | RP – OT | June | Kaia has accepted to resign due to ongoing health issues, the process will take some time to complete |
| 5.2 | Schedule changes | In Progress | RP |  | Seek approval from NMSA |
| 5.3 | NCD Registration locations | In Progress | NC, FR, HG | 2023 | At least one point of focus for registrations |
| 5.4 | - Community Inspector employment - Recruitment | In Progress | HG | 2023 | Inspectors have been recruited, progress now to identify sustainable employment options |
| 5.5 | NCD SCA Bank Account | COMPLETED | RP | 2021 | Register an account for the NCD SCA, can be done under MKA |
| 5.6 | Multiple MOU | In Progress | OT | 2023 | Draft an MOU with NMSA, Water Police, RPYC and the NCD SCA |
| 5.7 | Inspectors JD | In progress | RP |  | Circulate JD for adoption. |
| 5.8 | Inspector inductions | COMPLETED | RP, NMSA | 2021 | Submit names of Inspectors to NMSA for inductions. |
| 5.9 | Registration App | In Progress | RP | 2023 | NMSA reviewed and indicated to fund the project, however no action taken and NCD SCRB is considering purchasing. |
| 5.10 | Registration stickers | In Progress | RP | 2023 | Seeking locally produced stickers that fit the SCA requirements. Costing in progress |
| 5.11 | Safety stickers | In progress | RP | 2023 | Not a priority |
| 5.12 | Licensing card | In progress | RP | 2023 | Check ID printers for the registrar to print licenses for boat operators. |
| 5.13 | Fines | In Progress | RP, JB | 2023 | Discussions on management of fines and the process with Water Police |